|  | Nordic Resilience Communication | OFFER |
| --- | --- | --- |

| Date | Client | Client contact | Project number |
| --- | --- | --- | --- |
| 2026-05-05 | Team Neusta | Klaudia Kruger / André Conin | 1 |
| Project Nordic Market Entry & Positioning Partnership |  |  |  |

NORC x Safespring x Team Neusta

Team Neusta brings digital scale, engineering depth and transformation capacity.

NORC brings Nordic market understanding, strategic positioning, communication and trust-building.

Together, the ambition is to establish a credible and commercially viable position in the Nordic market.

# Engagement Principle

NORC is engaged to shape positioning, market entry and early-stage business development - not as a lead generation or sales execution provider.

# Phase 1 - START (90 + 90 days)

Objective:

Establish a clear, credible and testable Nordic market position

Investment:

EUR 4,500 / month (approx. 50,000 SEK)

Duration: 3 + 3 months

## Scope

1. Alignment & Market Hypothesis

Define ambition, priority markets and scope

Establish initial market entry hypotheses

2. Nordic Positioning

Develop Nordic value proposition

Messaging hierarchy and narrative

Positioning adapted to Nordic decision logic

3. Focus Areas (2-3 entry points)

Recommended initial focus:

Industrial AI & Digital Transformation

Digital Resilience & Secure Platforms

Public Sector / Critical Infrastructure

# Market Assets

Nordic presentation material

Core messaging and meeting narrative

Thought leadership angles

# Pilot Outreach (limited)

Testing positioning in selected dialogues

Feedback and iteration

# Out of Scope

Full-scale sales execution

Lead generation at scale

Campaign production

Local staffing or operational delivery

# Phase 2 - SCALE (3-9 months)

Objective:

Convert positioning into active business opportunities

## Scope

Go-to-market execution and prioritisation

Joint offer development (2-3 packaged offers)

Strategic meetings and opportunity shaping

Communication and thought leadership

Sales enablement and refinement

Investment (indicative)

EUR 7,000 - EUR 11,000 / month

Optional success-based component

# Phase 3 - SUSTAIN (long-term)

Objective:

Establish a stable and scalable Nordic presence

## Scope

Ongoing positioning and communication governance

Strategic account development

Market intelligence and adaptation

Long-term collaboration model

Investment (indicative)

From EUR 10,000 / month

# Recommended Approach

We strongly recommend starting with a focused scope (2-3 entry points), rather than introducing the full portfolio, to ensure clarity, relevance and early traction in the Nordic market.

# NORC - A Viable Solution

NORC helps organisations build communication resilience in complex environments by aligning strategy, leadership, brand, digital systems, and governance into one coherent operational capability.

# Viable Solutions - Nordic Special Operations Company

Viable Solutions translates strategy into operational effect through structures, systems, and capabilities that enable organisations to operate with clarity, speed, and resilience over time.

Läs mer på viablesolutions.se

# Contact

Anders Rasmusson

+46(0)707-266 098

contact@norc.agency